**ISSUE REPORT**

**country code Policy Development Process 3**

**on introduction of a Review Mechanism and**

**Retirement of country code Top Level Domains**

March 2017

Bart Boswinkel

Issue Manager ccPDP 3

**Table of Contents Page**

**Executive Summary** 3

**1. Introduction** 4

1.1 Background 4

1.2 Process 4

1.3 Readers’ Guide 5

**2. Recommendation**  6

2.1 Introduction 6

2.2 Summary of the issues identified 6

*2.2.1 Contextual information Review Mechanism*  7

*2.2.2 High Level overview of Issues pertaining to review mechanism* 8

*2.2.3 Contextual Information retirement of ccTLDs* 8

*2.2.4 High Level overview of Issues pertaining to Retirement*  9

2.3 PDP Initiation Threshold Criteria 9

2. 4 Opinion ICANN’s General Counsel 10

2.5 One or two PDPs? 11

2.6 Methodology: Working Groups 13

2.7 Recommendations of Issue Manager 14

**3. Uncertainty of approval of outcome by the ICANN Board**  16

**4. Structure of ccNSO PDP and tentative minimum timeline**. 17

4.1 Structure of the ccNSO Policy Development Process 17

4.2 Basic Schedule and Timeline 17

**5. Background material & References** 19

Annex A: Charter Working Group Review Mechanism ccTLDs 20

Annex B: Charter Working Group Retirement of ccTLDs 31

Annex C: Detailed Schedule and Timeline 39

Postscript 42 ccNSO Council Resolution 42

Adjusted timeline to reflect adopted order of work items 45

**Executive Summary**

In December 2015, the ccNSO Council discussed the need to launch a formal ccNSO Policy Development Processes to address the lack of policy with respect to retirement of ccTLDs and introduction of a Review Mechanism on issues pertaining to the delegation, transfer, revocation and retirement of ccTLDs. This discussion was grounded in the need to ensure the predictability and legitimacy of decisions with respect to the delegation, transfer, revocation and retirement of ccTLDs and to fill the lack of policy pertaining to the retirement of ccTLDs.

At its meeting on 16 June 2016 the ccNSO Council resolved:

1. Request an Issue Report in accordance with Annex B section 1 of the ICANN Bylaws. The Issue Report should address the following topics:
   1. Recommend whether the ccNSO should initiate the ccNSO Policy Development Process on the retirement of ccTLDs and Review Mechanism for decision pertaining to the delegation, transfer, revocation and retirement of ccTLDs.
   2. Advise whether to initiate one or two ccNSO Policy Development Processes, and the order in which the topics should be addressed.
   3. Advise whether to convene a Taskforce or use another method
2. To appoint an Issue Manager

In November 2016, the ccNSO Council further resolved to appoint a drafting team to develop charters and delineate the issues pertaining to the review mechanism and retirement of ccTLDs.

Following the discussions within the Council, feed-back and input from the community and the drafting team, the Issue Manager recommends:

1. The ccNSO Council initiates a ccNSO Policy Development Process to develop policies for a Review Mechanism and on the retirement of ccTLDs.
2. To initiate one (1) ccNSO Policy Development Process. It is further recommended that the initial focus needs to be on developing a Review Mechanism, which is considered the highest priority, in particular in light of the IANA Stewardship transition. Only then the focus should be on retirement, and, if needed, revisit the Review Mechanism to include decisions relating to the retirement of ccTLDs.
3. To appoint two working groups each with its own charter, working method and schedule.

**1. Introduction**

1.1 **Background**

At its meeting on 10 December 2015 the ccNSO Council discussed the launch of the formal ccNSO Policy Development Processes to address the lack of policy with respect to retirement of ccTLDs and introduction of a Review Mechanism[[1]](#footnote-1) on issues pertaining to the delegation, transfer, revocation and retirement of ccTLDs. This discussion was grounded in the need to ensure the predictability and legitimacy of decisions with respect to the delegation, transfer, revocation and retirement of ccTLDs. As already recommended by the ccNSO Delegation and Redelegation working group (DRDWG) in 2011[[2]](#footnote-2), the void or lack of policy relating to the retirement of ccTLDs needs to be filled by a policy developed by the ccNSO. However, at the time the DRDWG also recommended that such a ccNSO PDP should be launched following the development of a Framework of Interpretation of RFC 1591.

Following the initial discussions of the Council, input and feed-back was sought from the community at the Marrakesh, Helsinki and Hyderabad meeting. The community present at these meetings confirmed the need for developing a policy for a Review Mechanism and on retirement of ccTLDs. ,

At its meeting on 16 June 2016 the ccNSO Council resolved to request an Issue Report in accordance with Annex B section 1 of the ICANN Bylaws. The Issue Report should address the following topics:

1. Recommend whether the ccNSO should initiate the ccNSO Policy Development Process on the retirement of ccTLDs and Review Mechanism for decision pertaining to the delegation, transfer, revocation and retirement of ccTLDs.
2. Advise whether to initiate one or two ccNSO Policy Development Processes, and the order in which the topics should be addressed.
3. Advise whether to convene a Taskforce or use another method

**1.2 Process**

The general process framework for a ccNSO Policy Development Process is the following:

1. **Initiation of ccPDP.** The Council will need to vote on whether to initiate the PDP on the issues as defined. The basic document for this phase is the Issue Report.
2. **Comments Issue Report.** If the Council decides to initiate the ccPDP, comments on the issue(s) as defined in the Issue Report are sought.
3. **Preparing Recommendations.** Within the scope defined in the Issue Report and taking into account the comments received, community members will develop the recommended policy in the manner as determined by the ccNSO Council. The recommendations will be included in the Initial Report for public comment and then in the Final report.
4. **Decision-making on Recommendations by ccNSO.** Based on the Final Report the ccNSO Council and members of the ccNSO will need to vote on the proposed recommendations.

This general framework is the basis for the more detailed schedule for the ccPDP included in section 4, Schedule and Timeline for the upcoming ccPDP. This Issue Report is the basis for the ccNSO Council decision for initiation of the ccPDP.

**1.3 Readers’ Guide**

To inform the discussions of Council and broader community, three (3) separate but clearly interrelated questions were raised by the ccNSO Council:

1. Recommend whether the ccNSO should initiate the ccNSO Policy Development Process on the retirement of ccTLDs and Review Mechanism for decision pertaining to the delegation, transfer, revocation and retirement of ccTLDs.
2. Advise whether to initiate one or two ccNSO Policy Development Processes, and the order in which the topics should be addressed.
3. Advise whether to convene a Taskforce or use another method

The answers to these questions will be presented in the following order as part of the Recommendation (section 2) of this report. First, a high level overview of the issues pertaining to the review mechanism and retirement of ccTLDs is provided in section 2.2. The threshold criteria to initiate a PDP are presented in section 2.3 and the required Opinion of ICANN’s General Counsel is included in section 2.4.

The second Council questions, whether to combine the development of proposals pertaining to the Retirement of ccTLDs and Review Mechanism for decision regarding delegation, revocation, transfer and retirement of ccTLDs in one single formal policy development process, is discussed in section 2.5. This is followed (section 2.6) by the proposal to undertake the development effort in two working groups. The proposed charters of these working groups, including their respective scope of topics and proposed working methods are included in Annex A and B. The Recommendation to initiate the PDP itself is contained in section 2.7.

Under the Bylaws (Annex B section 2.g) the Issue Manager is required to advise whether the proposed policy that will be approved by the ICANN Board of Directors. This is (briefly) discussed in section 3.

The final two sections of this report, section 4 Structure of ccNSO PDP and tentative minimum timeline and section 5 References, are administrative in nature.

**2. Recommendation**

**2.1 Introduction**

The Bylaws (Annex B) require the Issue Manager to recommend to the ccNSO Council whether to initiate a ccPDP. To proceed the Issue Manager must first determine that the PDP Issue(s) identified to be addressed ( Section 2.2 ) meet threshold criteria defined in the Annex B (See section 2.3 below). The Bylaws (Annex B) also require that any such recommendation should include the opinion of ICANNs General Counsel as to whether the identified PDP Issues are within the scope of ICANN's mission and the scope of the ccNSO for policy making; implicate or affect an existing ICANN policy; and likely to have lasting value or applicability (see section 2.4. below).

In the final part of this section the recommendation of the Issue Manager is included as to whether the Council should move to initiate the PDP to address the identifies issues.

**2.2 Summary of the issues identified**

This section contains a summary of the main topics to be addressed. In Section 2.2.1 some contextual information is provided with relation to a Review Mechanism[[3]](#footnote-3) and section 2.2.2 provides a high level overview of the issues.

The issues pertaining to the retirement of ccTLDs, including IDN ccTLDs are summarized in Section 2.2.3 (contextual information) and section 2.2.4.

Following the discussions and comments on the Final Report of the ccNSO Delegation and Redelegation Working Group, the Framework of Interpretation WG, the initial proposals of the CWG-Stewardship, and input and feed-back from the community at the Marrakesh, Helsinki and Hyderabad meetings (when issues were intially presented to community), the issues were further refined by the ccNSO Drafting Team for charters under the ccPDP.

The results of the PDP(s) on Retirement and Review Mechanism should be available and be applicable to both IDN and ASCII ccTLDs. According to the Fast Track for the introduction of IDN ccTLDs and the overall recommended policy for their selection, IDN ccTLDs are ccTLDs, and hence the rules for delegation, revocation, transfer, and, in future, retirement of ccTLDs, apply to these ccTLDs. Note that the IDN ccPDP still awaits a Board vote, pending review of the EPSRP. However, until the Board has adopted the IDN ccTLD policy, the status of IDN ccTLD and therefore the scope of the anticipated PDP(s) will not be clearly delineated. Looking at IDN ccTLDs, one could also consider whether the IRP or the Review Mechanism to be developed should also apply to the IDN ccTLD string selection process. In this document references to ccTLDs are taken to refer to both ASCII and IDN ccTLDs.

**2.2.1 Contextual information Review Mechanism**

To date decisions taken as part of the processes for the delegation, transfer and revocation of ccTLDs are not subject to a review or appeal mechanism:

***RFC 1591***

According to RFC 1591, section 3.4, *the Internet DNS Names Review Board (IDNB), a committee established by the IANA, will act as a review panel for cases in which the* parties [Issue Manager: the Significantly Interested Parties[[4]](#footnote-4)] *can not reach agreement among themselves. The IDNB’s decisions will be binding.*

IANA has never established the IDNB (or any other entity) to review disputed cases.

***Framework of Interpretation***

With respect to the IDNB the FOIWG noted: *The FOI WG believes it is consistent with RFC 1591 (section 3.4) and the duty to act fairly to recognize the manager has the right to appeal a notice of revocation by the IANA Operator to an independent body.*

***CWG-Stewardship and CCWG-Accountability***

Following public comments on its first proposal, the CWG-Stewardship proposed that: *An appeal mechanism, for example in the form of an Independent Review Panel, for issues relating to the IANA functions.  For example, direct customers with non-remediated issues or matters referred by ccNSO or GNSO after escalation by the CSC will have access to an Independent Review Panel. The appeal mechanism will not cover issues relating to ccTLD delegation and re-delegation, which mechanism is to be developed by the ccTLD community post-transition.*

In addition, as part of the CCWG Accountability Proposal to enhance the Independent Review Process, the results of delegation/re-delegations are explicitly excluded[[5]](#footnote-5).

***ICANN Bylaws 1 October 2016***

According to latest version of the ICANN Bylaws (Section 4.2) Reconsideration: [[6]](#footnote-6)

*Section 4.2. RECONSIDERATION*

*(a) ICANN shall have in place a process by which any person or entity materially affected by an action or inaction of the ICANN Board or Staff may request ("****Requestor****") the review or reconsideration of that action or inaction by the Board. For purposes of these Bylaws, "****Staff****" includes employees and individual long-term paid contractors serving in locations where ICANN does not have the mechanisms to employ such contractors directly.*

*….*

*(d) Notwithstanding any other provision in this Section 4.2, the scope of reconsideration shall exclude the following:*

*(i) Disputes relating to country code top-level domain ("****ccTLD****") delegations and re-delegations;*

**2.2.2 High Level overview of Issues pertaining to review mechanism**

Given the expressed need for a review mechanisms and based on the community discussions, feed-back and comments to date, including but not limited to those with respect to the CWG-Stewardship and CCWG-Accountability proposals and related work, the following issues have been identified:

***Scope of the review mechanism***

1. *Which decisions and/or actions should be subject to a review mechanism?*
2. *Whose decisions and/or actions should be subject to a review mechanism?*
3. *What will be result / scope of the review decision? What powers will be bestowed upon review panel?*

***Standing at review mechanism***

1. *Who will have standing at a review mechanism?*
2. *Should a Review Mechanism be open and applicable to all ccTLDs?*

***What are the grounds?***

1. *Should the questions for a review be limited to questions about whether due process was followed in terms of a ccTLD delegation, transfer, revocation or retirement or should they be broader?*

***Rules and structure of review mechanism***

1. *What are the rules and procedures to be used?*
2. *Structure of panel and requirements and selection of panellist*

A more detailed overview of topics of the issues pertaining to the Review Mechanism is included in the proposed charter of WG 1 (Annex A).

* + 1. **Contextual Information retirement of ccTLDs**

To date, only a limited number of ccTLDs have been undelegated. The majority of these cases are recorded in the Delegation Redelegation working group (DRDWG) final report on the retirement of ccTLDs[[7]](#footnote-7). Since publication of this report in 2011 two more cases of retirement have occurred[[8]](#footnote-8). As the DRDWG has noted, although the frequency of retirements is very low, there is no policy in place regarding the retirement of ccTLDs, and the practices to date seem to provide an insufficient framework for such a critical activity.

Looking at the recorded cases of undelegation (including retirements), most cases appear to be initiated when the name of the country or territory was removed from the ISO 3166-1 list. Country names might be removed from ISO 3166-1 for various reasons[[9]](#footnote-9), for example:

* A country might change a significant part of its name, for example Burma (BU) was changed to Myanmar (MM) in 1989.
* A country may divide into two or more new ones, for example Czechoslovakia was divided into Czech Republic and Slovakia in 1993. Later CS was used as assigned code for Serbia and Montenegro. With the subsequent separation of Montenegro as a separate country the code CS got retired again.
* Two or more countries may merge for example Democratic Yemen (YD) and Yemen Arab Republic (YE) merged into the Republic of Yemen (YE) in 1990.

**2.2.4 High Level overview of Issues pertaining to Retirement**

Based on an initial analysis of the cases of retirement to date the following initial topics and issues emerge that among others need to be addressed:

1. ***Consistency of terminology***
2. ***What triggers a retirement of a ccTLD?***
3. ***Who triggers retirement process?***
4. ***Additional conditions for the retirement of a ccTLD?***
5. ***Compliance with conditions?***

A more detailed overview of topics of the issues pertaining to the Retirement of ccTLDs is included in the proposed charter of WG 2 (Annex B).

**2.3 PDP Initiation Threshold Criteria**

*The proposed issues raised for consideration*

The topics and issues raised for consideration are set out in section 2.2 above. This is an initial list to focus and guide the WG to achieve their goal of proposing a policy. A more detailed list is provided in section 1.3 in the charters of the proposed Working Groups (see section 2.6 below and Annex A and Annex B). In addition, if the WGs are aware of other topics and issues that are not listed and that in the view of a WG need to be addressed to achieve its goal, a WG should take these into consideration and inform the ccNSO Council and Issue Manager accordingly.

If topics and issues become apparent that are considered out of scope of the WG as defined in the charter of the WG, the Chair of the WG shall inform the ccNSO Council and Issue Manager accordingly. If the ccNSO Council concurs with the WG, the ccNSO Council is expected to take the necessary action to amend the scope of the WG.

*The identity of the party submitting the issue*

The ccNSO Council on behalf of broader ccNSO membership and ccTLD community. The topics and issue pertaining to the retirement of ccTLDs flow from the Delegation and Redelegation WG Final Report on Retirement of ccTLDs (2011) as adopted by the ccNSO Council. The topics and issues with respect to the review mechanism follow from the CWG-IANA Stewardship Transition and CCWG-Accountability WS 1 discussion processes, including the public comments from ccTLD on draft proposals and adoption of the respective final proposals by the ccNSO Council.

*How that party is affected by the issue*

ccTLD managers and others with an interest in the ccTLD are affected. Once the PDP(s) are concluded the predictability and legitimacy of decisions with respect to the delegation, transfer, revocation and retirement of ccTLDs are ensured and the policy void pertaining to the retirement of ccTLDs will be filled.

*Support for the issue to initiate the PDP*

There is significant support in the ccTLD community based on:

* The feed-back and comment received on the possible launch of the ccPDP during session at ICANN 55 56 and 57
* With respect to the review mechanism demonstrated through the public comment on the CWG- Stewardship Proposals and CCWG-Accountability and subject to agreement on the scope of such a mechanism
* Adoption by the Council, with the support of the community, of the recommendations of the Delegation and Redelegation Working Group Final report on retirement of ccTLDs.

**2. 4 Opinion ICANN’s General Counsel**

ICANN Bylaws Annex B, Section 2 specifies that every ccNSO Issue Report shall include "an opinion of the ICANN General Counsel regarding whether the issue is properly within the scope of the ICANN policy process and within the scope of the ccNSO[[10]](#footnote-10)."

The opinion of the ICANN General Counsel is that the development of policies for 1. review mechanism pertaining to the delegation, transfer, revocation and retirement of (IDN) ccTLDs and 2. Retirement of (IDN) ccTLDs for the selection and delegation of IDN ccTLDs are within the scope of the ccNSO and the ICANN policy process.

(Note: while the general subjects of review mechanism and retirement selection are within scope of the ccNSO, it should be noted that a few of the particular questions raised might not be within the scope of the ccNSO PDP, or within the scope of the ccNSO as defined in Annex C. For example, the question is raised whether a review mechanism should be open to all ccTLDs. Should that be accepted by non-ccNSO members?)

In reaching the determination on the question of scope, the ICANN Bylaws specify that the following considerations should be examined; whether:

1) The issue is within the scope of ICANN's mission;

2) Analysis of the relevant factors according to Section 10.6(b) and Annex C affirmatively demonstrates that the issues are within the scope of the ccNSO;

3) Implicates or affects an existing ICANN policy;

4) Is likely to have lasting value or applicability, albeit with the need for occasional updates, and to establish a guide or framework for future decision-making.

These considerations support the appropriateness of policy development for 1. a review mechanism pertaining to decision on delegation, transfer, revocation and retirement of ccTLDs and 2. retirement of ccTLDs being conducted within the ccNSO PDP. The policy pertaining to a Review Mechanism as outlined within this Issues Report does fall within ICANN’s Mission to ensure the stable and secure operation of the Internet’s unique identifier systems, which includes coordinating the allocation and assignment of names in the root zone of the DNS. The review mechanism is within the scope of ICANN’s mission because it would potentially develop a review mechanism pertaining to decisions on delegation, transfer, revocation and retirement of country code top level domains. Development of a review mechanism as outlined falls within the scope of the ccNSO policy development process as it intends to provide a review mechanism for decisions pertaining existing processes and procedures which are within the policy development remit of the ccNSO (delegation, transfer and revocation of ccTLDs) or will be developed as such (retirement of ccTLDs). In addition, it will bring clarity, update or change existing policy documentation[[11]](#footnote-11).

The retirement of ccTLDs is within ICANN's mission to coordinate at the overall level the Internet's domain name system, and scope of ccNSO policy development. It is a process, and procedure that potentially directly impacts ccTLDs, and hence the allocation and assignment of names in the root zone of the DNS.

* 1. **One or two PDPs?**

At its meeting on 10 December 2015 the ccNSO Council discussed the launch of the formal ccNSO Policy Development Processes to address the lack of policy with respect to retirement of ccTLDs and Review Mechanism on issues of delegation, revocation and retirement of ccTLDs. One of the questions of the ccNSO Council was whether to combine the development of policies under one formal Policy Development Process or initiate two separate but interrelated processes.

In line with the recommendations of the Delegation and Redelegation working group in 2011[[12]](#footnote-12), it was advised that a policy development process on retirement of ccTLDs should be launched once the Framework of Interpretation was concluded to fill the void of lack of policy and hence to increase the predictability and legitimacy of decisions pertaining to the retirement of ccTLDs.

At the request of Council, the secretariat prepared an overview of the different alternatives and associated timelines, taking into account the feed-back and input received at the Marrakesh, Helsinki and Hyderabad meeting.

These alternatives were presented to Council at its meeting on 12 May 2016:

1. The two PDPs (Review Mechanism and Retirement) run sequentially
2. One PDP with two sequential WG (Review Mechanism, Retirement)
3. One PDP with two Parallel WG (effectively the same as one PDP with one WG)

Analysis suggested that the major differences between the alternatives are:

* The Review Mechanism could be available to the community more quickly with separate PDPs (although decisions might need to be revisited in the light of work on retirement).
* Topics to be addressed and hence required skill set and expertise to resolve the issues might be more effectively used;
* Better availability of community members and a more manageable workload for the community.

The discussion on the applicability of Review Mechanism has focused on decisions on delegation, revocation and transfer of ccTLDs. However, the Review Mechanism could also be available for decisions pertaining to the retirement of ccTLDs. If the two policy development processes run separately this implies that:

* Alternative 1: the policy on Retirement should be concluded first, before the policy for the Review Mechanism is concluded or
* Alternative 2 The policy on the Review Mechanism should be revisited after its conclusion.

If the two topics are combined under one PDP it will have an impact on the initial scoping efforts and manageability of the process, however it avoids the major complication to revisit and review a recommended policy almost immediately after it is adopted (and potentially before its implementation has been completed).

With the successful conclusion of the IANA Stewardship Transition the community present at the Helsinki meeting expressed a strong view that a Review Mechanism should be in place rather sooner than later. It was felt that ensuring a redress mechanism for ccTLDs for the most critical decisions pertaining to a ccTLD: delegation, revocation, transfer and retirement is a high priority. Until such time as a policy has been developed, such a mechanism is unavailable, whilst other decisions or similar decisions affecting gTLDs are subject to review and redress.

Different sets of expertise and skill sets will most likely be required to address the two issues. For the Retirement ccPDP a thorough understanding of RFC 1591, ISO 3166 rules, and the DRDWG final report is required, as well as operational understanding of the DNS. For the ccPDP on a Review Mechanism, a thorough understanding of RFC 1591 and the FOI, and legal expertise will be required, as well as a thorough understanding of the currently existing appeal mechanisms and proposed CCWG Accountability mechanism (including the IRP and other mechanisms proposed by the CCWG Accountability).

Following the initial discussions of Council, and the input and feed-back received it is recommended to initiate one (1) ccNSO Policy Development Process. In addition it is recommended that the initial focus needs to be on developing a Review Mechanism, which is considered the highest priority, in particular in light of the IANA Stewardship transition. Only then the focus should be on retirement, and, if needed, revisit the Review Mechanism to include decisions relating to the retirement of ccTLDs.

**2.6 *Methodology: Working Groups***

The Bylaws permit the ccNSO Council to appoint a Task Force to gather information documenting the positions of the various parties or groups as specifically and comprehensively as possible, to facilitate meaningful and informed deliberation by the Council on the issue(s).

To convene a Task Force, the Council must:

1. Identify Task Force members (including the required participation of two Representatives of the Regional Organizations) and formally request GAC participation;
2. Develop a charter or terms of reference that must specify:
   1. The issues to be addressed by the Task Force;
   2. The time line to be followed by the Task Force;
   3. Any specific instructions for the Task Force, including whether or not the Task Force should solicit the advice of outside advisors on the issue.

Alternatively, in the event the ccNSO Council does not convene a Task Force:

1. Each Regional Organization is invited? to appoint a representative to solicit the Region’s view on the issue, within the time designated in the PDP Time Line;
2. The Council must formally request the Chair of the GAC to offer opinion or advice; and
3. The Council may take other steps to assist in the PDP, for example, appointing particular individual(s), to gather information and to assist the Issue Manager.

Given the issue(s) to be resolved and the cross cutting interests involved, and taking into account the experiences to date with Working Groups in general and under the previous PDP in particular, the Issue Manager concludes that any potential benefits of appointing a Task Force are not outweighed by its inherent limitations. The ccNSO Council is therefore advised not to appoint a Task Force, but to appoint two working groups each with its own charter, working method and schedule.

The goal of the first working group (WG 1) is to report on and recommend a feasible policy for a review mechanism with respect to decisions pertaining to the delegation, transfer, revocation and retirement of the Top Level Domains associated with the country codes assigned to countries and territories listed in the ISO 3166-1 and within the framework of the ccNSO Policy Development Process.

The goal of the second working group (WG2) is to report on and recommend a feasible policy for the retirement of the delegated Top Level Domains associated with the country codes assigned to countries and territories listed in the ISO 3166-1 within the framework of the ccNSO Policy Development Process.

The working groups are to be guided by the scope as defined in its charter. In addition to the members from the ccTLD community, the Council should invite each of the Regional ccTLD Organisations, the ALAC, GAC, GNSO and SSAC to participate and to appoint at least one participant to each of the Working Groups, in accordance with their own rules and procedures. The Issue Manager further recommends that at least one staff member from PTI is invited to each of the WGs and that an expert on ISO 3166 standardisation should be invited at least for the WG on retirement of ccTLDs.

The working methods and internal decision-making are also described in the charter for the Working Groups. The charters as proposed are included as Annex A and B and have been developed by the ccNSO charter drafting team[[13]](#footnote-13)

The Issue Manager further recommends that the second working group (on retirement of ccTLDs) will be launched once working group 1 on the review mechanism has concluded its work with respect to delegation, transfer and revocation of ccTLDs. After Working group 2 has concluded its work, working group 1 will need to revisit its work to update its proposed policy to build on the proposals of Working group 2. The high-level timeline is included in section 4 and in detail in Annex C.

**2.7 Recommendations of Issue Manager**

According to the Bylaws (Annex B section 2.e), the Issue Manager is required to make a Recommendation as to whether the Council should move to initiate the PDP for the issues identified in this report.

The ccNSO Council asked the Issue Manager to:

1. Recommend whether the ccNSO should initiate the ccNSO Policy Development Process on the retirement of ccTLDs and Review Mechanism for decision pertaining to the delegation, transfer, revocation and retirement of ccTLDs.
2. Advise whether to initiate one or two ccNSO Policy Development Processes, and the order in which the topics should be addressed.
3. Advise whether to convene a Taskforce or use another method

*Recommendation 1: Should the ccNSO Council initiate a ccPDP to develop policy for a Review Mechanism and on the retirement of ccTLDs?*

Based on a review of the issues, considering that the Threshold Criteria are met, and taking into account General Counsel’s opinion, the Issues Manager recommends that the ccNSO Council initiates a ccNSO Policy Development Process to develop policies for a Review Mechanism and on the retirement of ccTLDs.

*Recommendation 2: Should the ccNSO Council initiate one or two ccNSO Policy Development Processes, and in what order should the topics be addressed?*

Following the initial discussions of Council, and the input and feed-back received it is recommended to initiate one (1) ccNSO Policy Development Process. It is further recommended that the initial focus needs to be on developing a Review Mechanism, which is considered the highest priority, in particular in light of the IANA Stewardship transition. Only then the focus should be on retirement, and, if needed, revisit the Review Mechanism to include decisions relating to the retirement of ccTLDs.

*Recommendation 3: Should the ccNSO Council convene a Taskforce or use another method?*

Any potential benefit of appointing a Task Force is outweighed by its inherent limitations. The ccNSO Council is advised not to appoint a Task Force, but instead to appoint two working groups each with its own charter, working method and schedule.

**3. Uncertainty of approval of outcome by the ICANN Board**

The Bylaws (Annex B section 2.g) require the Issue Manager to advise as to whether the ccNSO Policy Development Process is likely to result in a proposed policy that will be approved by the ICANN Board of Directors. To date, no substantive discussion on these issues has taken place, nor are they likely to take place before any substantial output has been produced.

**4. Structure of ccNSO PDP and tentative minimum timeline**.

**4.1 Structure of the ccNSO Policy Development Process**

At a high level and based on the description of the ccNSO Policy development Process in Annex B of the ICANN Bylaws, 8 phases should be distinguished. However, the four last ones, as of the Board vote up until implementation, are beyond the control of the ccNSO community.

1. **Initiation of ccPDP.** According to the ICANN By-laws Appendix B, section 3, the Council will need to vote on whether to initiate the PDP on the issues as defined. The basic document or this phase is the Issue Report.
2. **Comments Issue Report.** If the Council decides to initiate the ccPDP, the first step is to seek comments on the issue(s) as defined in the Issue Report. Comments will then be compiled by the Issue Manager and, together with the Issue Report, used as starting point for developing the recommendations.
3. **Preparing Recommendations.** Within the scope defined in the Issue Report and taking into account the comments received, community members will develop the recommended policy in the manner as determined by the ccNSO Council (through a Task force or in another way). The recommendations will be included in the Initial Report that will be open for public comments. These comments will be reviewed and the appropriate comments, to be determined by the Issue Manager, will be added to the Initial report, to create the Final report.
4. **Decision making on Recommendations by ccNSO.** Based on the Final Report the Council shall work towards achieving recommendations to be submitted to the ICANN Board of Directors for adoption. The process would require support of the recommended policy by a supermajority (66% or more) of the members of the ccNSO who at the end of the process lodge a vote.

**4.2 Basic Schedule and Timeline**

Assuming the ccNSO PDP will be structured around two working groups, a tentative minimal timeline for these phases is listed below. This timeline is based on experience to date with the previous PDP and working groups like the ccNSO FOIWG and DRDWG.

Assuming the scope of this ccNSO PDP is focused e.g. has a relatively limited scope, the ccNSO PDP will take at a minimum 21 months. However the actual duration will be determined by the duration of the effective active discussion/ work period. For purposes of this timeline it is estimated at 4 months per WG and 3 months for community members (minimum of 2 public consultations). Experience has shown that actively discussing an issue at WG level from start to finish in 4 months is optimistic.

A more detailed Schedule and Timeline is included in Annex C

**Schedule and Timeline**

|  |  |  |  |
| --- | --- | --- | --- |
| **Phase** | **Description** | **Expected starting date and minimal duration if applicable.** | **Cumulative Timeline** |
| Phase 1: Initiation of ccPDP | Decision of Council to initiate PDP and launch Phase 3 by call for volunteers | March 2017 |  |
| Phase 2: Comments on Issue PDP | Publish Issue report, call for volunteers, inform SO/ACs etc. | Minimum 2 months | March- May 2017 |
| Phase 3: Preparing Recommendations | Preparing Initial and Final proposals by WGs , including at a minimum one (1) Public Comment on combined output | Minimum 18 months  (9 months WG 1, 7 months WG 2, Interim Report Issue Manager 2 Months . WG 1 and WG 2 partially parallel) | May 2017 – March 2019 |
| Phase 4: decision making (Council and Members). | Decision making procedures and requirements as prescribed for the Council and Members | Expected duration: at a minimum 2 months, maximum 4 months. Start post ccNSO members meeting | November 2018- January 2019 |
| Phase 5: Submission Board report | Issue manager and Council to prepare Board report | 0.5 Month | January 2019 |
| Phase 6: Board vote |  |  |  |
| Phase 7: Supplemental Recommendation |  |  |  |
| Phase 8: Implementation |  |  |  |

**5. Background material & References**

In preparing the Issue Report, and, in proposing a time line for conducting each stage of the ccPDP the following documents provided guidance and were taken into account:

* The ccNSO Delegation and Redelegation working group Final report on retirement of ccTLDs, 07 march 2011 (<http://ccnso.icann.org/workinggroups/drd-wg-retirement-report-07mar11-en.pdf)>
* RFC 1591 (<https://www.ietf.org/rfc/rfc1591.txt> )
* ISO 3166 standard (<http://www.iso.org/iso/country_codes)>
* The ccNSO Framework of Interpretation working group Final Report, (<http://ccnso.icann.org/workinggroups/foi-final-07oct14-en.pdf> )
* CWG-Stewardship Final Report, Annex O: ccTLD Appeals Mechanism Background and supporting Findings Sections 1414- 1428.
* and any other matters that the Issues Manager considers to be of relevance.

**Annex A: Charter Working Group 1: Review Mechanism**

**Charter Working Group Review Mechanism of ccTLDs**

**0. Contextual Background Information Review Mechanism[[14]](#footnote-14)**

To date decisions taken as part of the processes for the delegation, transfer and revocation of ccTLDs are not subject to a review or appeal mechanism:

***RFC 1591***

According to RFC 1591, section 3.4, *the Internet DNS Names Review Board (IDNB), a committee established by the IANA, will act as a review panel for cases in which the* parties [Issue Manager: the Significantly Interested Parties[[15]](#footnote-15)] *can not reach agreement among themselves. The IDNB’s decisions will be binding.*

This IDNB was never established by IANA, or any other entity.

***Framework of Interpretation***

With respect to the IDNB the FOIWG noted: *The FOI WG believes it is consistent with RFC 1591 (section 3.4) and the duty to act fairly to recognize the manager has the right to appeal a notice of revocation by the IANA Operator to an independent body.*

***CWG-Stewardship and CCWG-Accountability***

Following public comments on its first proposal, the CWG-Stewardship proposed that: *An appeal mechanism, for example in the form of an Independent Review Panel, for issues relating to the IANA functions.  For example, direct customers with non-remediated issues or matters referred by ccNSO or GNSO after escalation by the CSC will have access to an Independent Review Panel. The appeal mechanism will not cover issues relating to ccTLD delegation and re-delegation, which mechanism is to be developed by the ccTLD community post-transition.*

In addition, as part of the CCWG Accountability Proposal to enhance the Independent Review Process, the results of delegation/re-delegations are explicitly excluded[[16]](#footnote-16).

***ICANN Bylaws 1 October 2016***

According to latest version of the ICANN Bylaws (Section 4.2) Reconsideration: [[17]](#footnote-17)

#### Section 4.2. RECONSIDERATION

#### (a) ICANN shall have in place a process by which any person or entity materially affected by an action or inaction of the ICANN Board or Staff may request ("**Requestor**") the review or reconsideration of that action or inaction by the Board. For purposes of these Bylaws, "**Staff**" includes employees and individual long-term paid contractors serving in locations where ICANN does not have the mechanisms to employ such contractors directly.

*….*

*(d) Notwithstanding any other provision in this Section 4.2, the scope of reconsideration shall exclude the following:*

*(i) Disputes relating to country code top-level domain ("****ccTLD****") delegations and re-delegations;*

Following the discussions and comments on the Framework of Interpretation and – later – on the initial proposals of the CWG-Stewardship, and input and feed-back from the community at the Marrakesh and Helsinki meeting, the community present was of the view that a policy needs to be developed with respect to the introduction of a review mechanism. Based on the consultations to date the community considers this the highest priority, in particular in light of the IANA Stewardship transition.

**1. Goal, Scope and issues to be addressed**

1.1 Goal

The goal of the working group (WG) is to report on and recommend a policy for a review mechanism with respect to decisions pertaining to the delegation, transfer, revocation and retirement of the delegated Top Level Domains associated with the country codes assigned to countries and territories listed in the ISO 3166-1 and within the framework of the ccNSO Policy Development Process.

1.2 Scope

To achieve its goal, the WG shall initially focus on and be guided by the topics and issues listed below in section 1.3. If other topics and issues become apparent that are not listed and that in the view of the WG need to be addressed to achieve its goal, the WG should take these into consideration and inform the ccNSO Council and Issue Manager accordingly.

As this WG will undertake its activities within the framework of the ccNSO Policy Development Process, the limitations with respect to the scope of a ccPDP, Article 10 and Annexes B and C to the ICANN Bylaws, shall also limit the scope of the WG’s work.

If topics issues become apparent that are considered out of scope of the WG, the Chair of the WG shall inform the ccNSO Council and Issue Manager accordingly. If the ccNSO Council is also of the opinion it is outside the scope of the WG, it is expected to deal with it appropriately.

**1.3 High Level overview of topics and Issues pertaining to review mechanism**

Given the expressed need for a review mechanisms and based on the community discussions, feed-back and comments to date, including but not limited to those with respect to the CWG-Stewardship and CCWG-Accountability proposals and related work, the following issues have been identified:

**Scope of the review mechanism**

1. *Which decisions and/or actions should be subject to a review mechanism?*
2. *Whose decisions and/or actions should be subject to a review mechanism?*

With regard to these questions, RFC 1591 section 3.4 called for the creation of the IDNB: [The IDNB] *will act as a review panel for cases in which the parties [ i.e the Significantly Interested Parties] cannot reach agreement among themselves. The IDNB’s decisions will be binding.* This assumes that disputes among Significantly Interested parties (as defined in the Framework of Interpretation) are subject to a binding review mechanism. The IDNB has never been established.

Following the Framework of Interpretation of RFC 1591[[18]](#footnote-18), recognising that ultimate authority on public policy for any country is its government and legislature, nothing in the FOI is intended to, or should be taken to constrain or limit applicable law in respect to matters relating to country-code or IDN cc Top Level Domains, or in the state of incorporation/place of business of the IANA operator.

Further, the FOI WG *believed that it is consistent with RFC 1591 (section 3.4) and the duty to act fairly to recognize the manager has the right to appeal a notice of revocation by the IANA Operator to an independent body.*

*3. Should a Review Mechanism be open and applicable to all ccTLDs?*

*4. What will be result / scope of the review decision? What powers will be bestowed upon review panel?*

Assuming the introduction of a review mechanism, the scope of the decision of the review will need to be defined.

**Who will have standing at a review mechanism?**

**What are the grounds?**

Should the questions for a review be limited to questions whether due process was followed in terms of a ccTLD delegation, transfer, revocation or retirement or should they be broader?

**Rules and structure of review mechanism**

1. *the rules and procedures to be used?*
2. *Structure of panel and requirements and selection of panelist*

As part of the review mechanism proposals the structure of the panel (for example how many panelists, should there be a standing panel, or selection from a pool of panelists) and the requirements and selection of panelists need to be developed

Depending on scope of the decisions for review, the choice of law may be considered relevant to ensure the consistency with RFC 1591 and the Framework of Interpretation. According to the FOIWG, *“recognizing that ultimate authority on public policy for any country is its government and legislature, nothing in the FOI is intended to, or should be taken to constrain or limit applicable law in respect to matters relating to country-code or IDN string, or in the state of incorporation/place of business of the IANA operator.”*

# **2. The WG**

## **Members and other participants of the WG**

## The WG is open to members who are representatives of ccTLDs, participants from other stakeholder groups, observers and experts.

## Members, participants, and experts commit to participate actively and regularly in the work of the WG and are expected to have at least a basic understanding of the reference material (section 6).

Once appointed all participants in the WG will be subscribed to a mailing list. The mailing list will be archived after closure of the WG.

The names and affiliation of the WG members and other participants will be published on a dedicated WG page on the ccNSO website.

At any time WG members, participants, observers and experts may resign from the WG, by informing the Chair of the WG, who will then inform the ccNSO Council. After receiving a notification the ccNSO Council may seek a replacement.

***2.1.1 Members***

The working group should have at least 10 members who are representatives from ccTLD managers or their nominees (at least two (2) from each of the 5 ICANN Geographic Regions). With respect to members of the WG there is no requirement for a ccTLD to be a ccNSO Member. If fewer than two (2) nominations are received from a Geographic Region, the ccNSO Council will actively encourage additional nominations from those regions. Members are appointed by the ccNSO Council in accordance with the general rules and procedures of the ccNSO for working groups[[19]](#footnote-19).

The expectation is that any ccTLD that wishes to be actively involved in the WG will be allowed to do so.

The WG members shall nominate a chair and alternate chair from the members of the Working Group, who will then be appointed by the ccNSO Council.

***2.1.2 Participants, experts and observers to the WG***

In addition, the WG is open to participants, who shall not be considered members of the WG. Participants are entitled to participate on equal footing with members, unless the charter states otherwise. The ccNSO Council will request the following stakeholders to appoint at least one participant:

* Each of the Regional Organisations as defined in Section 10.5 of the ICANN Bylaws;
* ALAC
* GAC
* GNSO
* SSAC

*Experts to the WG*

The ccNSO Council may also invite and appoint experts as advisors to the WG. Experts shall not be considered members of the WG, but are entitled to participate on an equal footing in their area of expertise. The Council will at least invite the following persons:

* PTI staff
* Expert on the ISO 3166-1 list.

*Observers*

The WG will have the following observers:

* The Issue Manager for the ccPDP
* Any person appointed as observer by the chair of the WG

***2.1.3 Staff Support***

ICANN will be requested to provide adequate staff support to the WG

**2.2 Chair and vice-chair**

At the nomination of the members of the WG, the Chair and vice-chair of the WG will be appointed by the ccNSO Council. The chair and vice-chair should be members of the Working Group.

The Chair together with the vice-chair, will manage the ongoing activities of the WG and ensure an appropriate working environment by:

* Promptly sharing relevant information with the entire WG.
* Planning the work of the WG to meet the WG goals and leading the WG through its discussions.
* Regularly assessing and reporting on the progress of the WG to the Council and broader community.
* Keeping track of WG participation. Where a WG member does not regularly participate, the Chair will reach out to the member to engage that person in the WG. If, after a conversation that member does not regularly participate, the Chair will advise the Council, so that further steps can be taken to resolve the situation.

The Chair is the representative of the WG. If the Chair of a WG is not a member of the ccNSO Council, the ccNSO Council will appoint a ccNSO Council liaison, to act as an intermediary between the WG and the ccNSO Council or invite the chair to Council meetings to regularly inform the Council on progress made, take questions and participate in any deliberations related to the WG.

The chair and vice-chair will regularly inform the broader community on progress of the WG and seek (informal) feed-back from the community.

# **Operations of the WG**

## **Working Methods**

The first work item of the WG is to develop and agree on its working methods that will guide how the WG intends to conduct its business. These working methods will be made publicly available and be guided by the following principles:

* The meetings will rotate from a timing perspective to share the burden as the membership is distributed over different time zones.
* No firm decisions are taken during any single meeting without the substance of those decisions having been discussed and open for review / consideration by those that may not have been present during the meeting.
* Efforts should be made to ensure that non-native English speakers can participate on an equal basis in the discussions
* The WG will consider public comments and other input as appropriate, and at its reasonable discretion.
* The Secretariat will set up conference calls, maintaining mailing lists, etc. at the direction of the chair and vice-chair of the WG. At the request of the chair the Secretariat or other ICANN staff will also provide other forms of assistance, for example providing advice or an expert opinion.
  1. **Internal Decision making**

In developing its output – guideline for operations, working method, work plan and any reports or papers - the WG shall seek to act by consensus. The Chair may make a call for consensus. In making such a call, the chair should always make reasonable efforts to involve at a minimum all members of the WG. The chair shall be responsible for designating each position as having one of the following designations:

* Full Consensus - a position where no minority disagrees; identified by an absence of objection
* Consensus – a position where a small minority disagrees, but most agree

In the absence of Full Consensus, the Chair should allow for the submission of minority viewpoint(s) and these, along with the consensus view, shall be included in the report, paper or other relevant deliverable.

In rare cases, the Chair may decide to use of a poll to assess the level of support for a recommendation. However, care should be taken in using polls: they should not become votes, as there are often disagreements about the meanings of the poll questions or of the poll results. Such a poll shall be limited to the members, unless the chair decides otherwise.

Any person on the WG who disagrees with the consensus-level designated by the Chair, or believes that her/his contributions have systematically been ignored or discounted, should first discuss the circumstances with the Chair. If the matter cannot be resolved satisfactorily, the person should discuss the situation with the Chair of the ccNSO or a person designated by the Chair of the ccNSO.

If no consensus can be reached by the WG, the Chair of the WG will submit a Chair’s Report to the ccNSO Council and Issue Manager. In this report the Chair shall document the issues that are considered contentious, the process that was followed to try to reach a consensus position and suggestions to mitigate those issues, if any. If, after implementation of the mitigating measures, consensus still cannot be reached, the Chair shall prepare a Final Chair’s Report documenting the processes that was followed to reach consensus and this Final Chair’s Report will be deemed to replace the Final Paper. In this case, the ccNSO Council, advised by the Issue Manager, may decide to close the WG, or take mitigating measures, for example changing the charter and reconstitute a WG based on the new charter.

**3.3 Standards of Behaviour**

The persons on the WG are expected to behave in a mature and professional way when conducting its business. This includes, but is not limited to communicating with the fellow membership professionally and ensuring that the WG remains inclusive and productive. To resolve incidents of non-professional communication the following steps should be followed:

## Any concerns regarding the behaviour of one of the members, participants, observers or experts should first be raised with that person.

## If the issue is not satisfactorily resolved, a formal complaint may be raised with the Chair of the WG, who will attempt to mediate.

## If that is not possible, or if the complaint is sufficiently serious in nature, the Chair of the WG is empowered to restrict the participation of the person if in the chairs view the continued participation would not be appropriate and/or would seriously disrupt the working group from conducting its business.

## Generally, a person should first be warned privately, and then warned publicly before such the restriction is put into effect; only in extreme circumstances to be determined by the chair and vice-chair together, this restriction may be put in effect immediately.

If a WG Member disagrees with an imposed restriction, or the complainant disagrees with a restriction (or the lack of one), or there are other matters regarding the complaint that cannot be resolved satisfactorily, the participant, complainant, or the Chair of the WG may raise the issue with the Chair and Vice-Chairs of the ccNSO Council or their designate(s). They will review the matter and then decide. The ccNSO Council, WG Chair, WG person and complainant shall be informed accordingly.

4. Deliverables

4. 1. Working Method & Work Plan

The WG is expected to develop its working methods and a work plan first. The working methods should provide guidance on how the WG intends to conduct its business (see section 3.1). The work plan should include at a minimum, where feasible, timelines and expected outputs of the WG, based on the deliverables outlined in this Charter. Purpose of the work plan is to inform the community and ccNSO on the expected progress and anticipated schedule of public consultations.

Once the work plan is completed, the Time Line as set forth in section 6 shall be updated and published. If in the course of conducting its business the WG or the chair of the WG is of the view that the Time Line is untenable, the chair will inform the ccNSO Council and Issue Manager. The chair will then also suggest an adjusted Time Line to be adopted by the WG. Once adopted, the chair will inform the ccNSO Council and Issue Manager and the adjusted Time Line will be published.

4.2 WG Interim Paper

The WG shall develop and publish for public consultation an Interim Paper, which shall, at a minimum, include proposals to address the topics and issues identified in the Issue Report, an impact analysis of the proposals and any documentation necessary to make the proposals effective. The Interim Paper shall also contain a review and analysis of comments made on the Issue Report, if any, with respect to the retirement of ccTLDs. The Interim Paper shall be published for public consultation on the ICANN website following the guidelines for public consultations. The consultation should be scheduled in such a manner that it also allows for a public discussion with the relevant stakeholders at a designated ICANN meeting. The chair of the WG will send the Interim Paper to the Issue Manager of the ccPDP.

4.3 WG (draft) Final Paper

After conclusion of the public consultation on the Interim Paper, the WG shall prepare a (draft) Final Paper reflecting the Interim Paper, the comments received on the Interim Paper from the public consultation period.

If the WG is of the view that an additional public consultation is appropriate, it will prepare a draft Final Paper to be published for public consultation on the ICANN website and following the guidelines for public consultations. The consultation should be scheduled in such a manner that it also allows for a public discussion with the relevant stakeholders at a designated ICANN meeting. After conclusion of the public consultation on the draft Final Paper, the WG shall prepare its Final Paper that reflects the draft Final Paper, the comments received and how they have been taken into consideration by the WG, if at all.

The Final Paper will include the proposed policy recommendations. This Final Paper shall be published within fourteen (14) days after adoption of the paper by the WG and conveyed to the chairs of the ccNSO and GAC and the Issue Manager of the ccPDP. The Issue Manager shall include the Final Paper in the Interim Report of the ccPDP.

# **5 Miscellaneous**

**5.1 Omission in or unreasonable impact of Charter**

If this charter does not provide sufficient guidance and/or the impact of the charter is found to be unreasonable for conducting the business of the WG, the Chair has the authority to determine a proper course of action to mitigate the issue. Such action may, for example, consist of a modification to the Charter to address the omission or its unreasonable impact, in which case the Chair(s) may propose such modification to the ccNSO Council and Issue Manager. A modification shall only be effective after adoption of the amended by the ccNSO and after publication of the amended Charter. The chair of the WG shall exercise reasonable discretion with respect to question as to whether this charter does not provide guidance and/or the impact of the charter is unworkable with respect to the conduct of business of the WG.

## **5.2 Closure of the Working Group**

If the WG determines that it has completed its work, or if the WG cannot achieve its goal(s) the Final Chair Report, it will submit a Final Paper to the ccNSO Council and Issue Manager. This report should include a recommendation on the time to close the WG.

A WG is closed by a resolution of the ccNSO Council.

6. WG Time Line

|  |  |  |  |
| --- | --- | --- | --- |
| **Activity** | **Date\*** | **Closure\*** | **Minimum Duration** |
| **Establishment of Working Group** |  |  |  |
| **Publish Interim Report** |  |  | NA |
| **Public Comment on Interim Paper** |  |  | 40 days |
| **Publish Final Paper** |  |  | NA |
| **Closure of the WG** |  |  |  |

\* Latest date possible to meet minimum duration for public consultation period.

\*\* It is assumed in this schedule / time line the Final Paper is presented at an ICANN meeting.

7. References

* RFC 1591 (<https://www.ietf.org/rfc/rfc1591.txt> )
* The ccNSO Framework of Interpretation working group Final Report, (<http://ccnso.icann.org/workinggroups/foi-final-07oct14-en.pdf> )
* ISO 3166 standard (<http://www.iso.org/iso/country_codes)>
* CWG-Stewardship Final Report, Annex O: ccTLD Appeals Mechanism Background and supporting Findings Sections 1414- 1428, (<https://community.icann.org/download/attachments/53779816/FinalTransitionProposal_11June.pdf?version=1&modificationDate=1434047705000&api=v2> ).
* Issue paper to explore review mechanism: <https://community.icann.org/download/attachments/64068742/Issue%20to%20explore%20review%20mechanism%20January%202017.pdf?version=1&modificationDate=1491820322000&api=v2>

**Annex B: Charter Working Group 2: Retirement ccTLDs**

**Charter Working Group Retirement of ccTLDs**

**0. Contextual background information Retirement of ccTLDs**

To date, only a limited number of ccTLDs have been undelegated. The majority of these cases are recorded in final report of the Delegation Redelegation working group (DRDWG) on the retirement of ccTLDs[[20]](#footnote-20). Since publication of this report in 2011 two additional cases of retirement have occurred[[21]](#footnote-21). With respect to the retirement of ccTLDs the DRDWG noted, although retirements are very rare it is a very critical recommendation ICANN can make and as a policy based organisation, a proper policy should be in place.

Looking at the recorded cases of undelegation (retirement), most cases appear to be initiated when the name of the country or territory was removed from the ISO 3166-1 list. Country names might be removed from ISO 3166-1 for various reasons[[22]](#footnote-22) and retirement policy needs to consider different possible scenarios. Looking at historical cases might provide a useful starting point for the working group, for example:

* A country might change a significant part of its name, for example Burma (BU) was changed to Myanmar (MM) in 1989.
* A country may divide into two or more new ones, for example Czechoslovakia was divided into Czech Republic and Slovakia in 1993. Later CS was used as assigned code for Serbia, which caused all kinds confusion worldwide. With the subsequent separation of Montenegro as a separate country the code CS got retired again.
* Two or more countries may merge for example Democratic Yemen (YD) and Yemen Arab Republic (YE) merged into the Republic of Yemen (YE) in 1990.

**1. Goal, Scope and issues to be addressed**

1.1 Goal

The goal of the working group (WG) is to report on and recommend a policy for the retirement of the delegated Top Level Domains associated with the country codes assigned to countries and territories listed in the ISO 3166-1 within the framework of the ccNSO Policy Development Process.

1.2 Scope

To achieve its goal, the WG shall initially focus on and be guided by the topics and issues listed below in section 1.3 If other topics and issues become apparent that are not listed and that in the view of the WG need to be addressed to achieve its goal, the WG should take these into consideration and inform the ccNSO Council and Issue Manager accordingly.

As this WG will undertake its activities within the framework of the ccNSO Policy Development Process, the limitations with respect to the scope of a ccPDP, specifically by Article 10 and Annexes B and C to the ICANN Bylaws shall also limit the scope of the WG’s work.

If topics issues become apparent that are considered out of scope of the WG, the Chair of the WG shall inform the ccNSO Council and Issue Manager accordingly. If the ccNSO Council is also of the opinion it is outside the scope of the WG, it is expected to deal with it appropriately.

**1.3 High Level overview of topics and Issues pertaining to Retirement**

Based on an initial analysis of the cases of retirement to date the following initial topics and issues emerge that, among others, may need to be addressed:

* Consistency of terminology
* What triggers a retirement?
* Who triggers retirement process?
* Additional conditions for retirement of a ccTLD?

What are conditions for actual retirement of a ccTLD? Is the occurrence of a triggering event sufficient or should additional requirements be in place?

* Compliance with conditions?

Assuming retirement of a ccTLD is conditional, who will monitor, and who will be held accountable, if at all, if requirements are not met?

# **2. The WG**

## **Members and other participants of the WG**

## The WG is open to members who are representatives of ccTLDs, participants from other stakeholder groups, observers and experts.

## Members, participants, and experts commit to participate actively and regularly in the work of the WG and are expected to have at least a basic understanding of the reference material (section 6).

Once appointed all participants in the WG will be subscribed to a mailing list. The mailing list will be archived after closure of the WG.

The names and affiliation of the WG members and other participants will be published on a dedicated WG page on the ccNSO website.

At any time WG members, participants, observers and experts may resign from the WG, by informing the Chair of the WG, who will then inform the ccNSO Council. After receiving a notification the ccNSO Council may seek a replacement.

***2.1.1 Members***

The working group should have at least 10 members who are representatives from ccTLD managers or their nominees (at least two (2) from each of the 5 ICANN Geographic Regions). With respect to members of the WG there is no requirement for a ccTLD to be a ccNSO Member. If fewer than two (2) nominations are received from a Geographic Region, the ccNSO Council will actively encourage additional nominations from those regions. Members are appointed by the ccNSO Council in accordance with the general rules and procedures of the ccNSO for working groups[[23]](#footnote-23).

The expectation is that any ccTLD that wishes to be actively involved in the WG will be allowed to do so.

The WG members shall nominate a chair and alternate chair from the members of the Working Group, who will then be appointed by the ccNSO Council.

***2.1.2 Participants, experts and observers to the WG***

In addition, the WG is open to participants, who shall not be considered members of the WG. Participants are entitled to participate on equal footing with members, unless the charter states otherwise. The ccNSO Council will request the following stakeholders to appoint at least one participant:

* Each of the Regional Organisations as defined in Section 10.5 of the ICANN Bylaws;
* ALAC
* GAC
* GNSO
* SSAC

*Experts to the WG*

The ccNSO Council may also invite and appoint experts as advisors to the WG. Experts shall not be considered members of the WG, but are entitled to participate on an equal footing in their area of expertise. The Council will at least invite the following persons:

* PTI staff
* Expert on the ISO 3166-1 list.

*Observers*

The WG will have the following observers:

* The Issue Manager for the ccPDP
* Any person appointed as observer by the chair of the WG

***2.1.3 Staff Support***

ICANN will be requested to provide adequate staff support to the WG

**2.2 Chair and vice-chair**

At the nomination of the members of the WG, the Chair and vice-chair of the WG will be appointed by the ccNSO Council. The chair and vice-chair should be members of the Working Group.

The Chair together with the vice-chair, will manage the ongoing activities of the WG and ensure an appropriate working environment by:

* Promptly sharing relevant information with the entire WG.
* Planning the work of the WG to meet the WG goals and leading the WG through its discussions.
* Regularly assessing and reporting on the progress of the WG to the Council and broader community.
* Keeping track of WG participation. Where a WG member does not regularly participate, the Chair will reach out to the member to engage that person in the WG. If, after a conversation that member does not regularly participate, the Chair will advise the Council, so that further steps can be taken to resolve the situation.

The Chair is the representative of the WG. If the Chair of a WG is not a member of the ccNSO Council, the ccNSO Council will appoint a ccNSO Council liaison, to act as an intermediary between the WG and the ccNSO Council or invite the chair to Council meetings to regularly inform the Council on progress made, take questions and participate in any deliberations related to the WG.

The chair and vice-chair will regularly inform the broader community on progress of the WG and seek (informal) feed-back from the community.

# **Operations of the WG**

## **Working Methods**

The first work item of the WG is to develop and agree on its working methods that will guide how the WG intends to conduct its business. These working methods will be made publicly available and be guided by the following principles:

* The meetings will rotate from a timing perspective to share the burden as the membership is distributed over different time zones.
* No firm decisions are taken during any single meeting without the substance of those decisions having been discussed and open for review / consideration by those that may not have been present during the meeting.
* Efforts should be made to ensure that non-native English speakers can participate on an equal basis in the discussions
* The WG will consider public comments and other input as appropriate, and at its reasonable discretion.
* The Secretariat will set up conference calls, maintaining mailing lists, etc. at the direction of the chair and vice-chair of the WG. At the request of the chair the Secretariat or other ICANN staff will also provide other forms of assistance, for example providing advice or an expert opinion.
  1. **Internal Decision making**

In developing its output – guideline for operations, working method, work plan and any reports or papers - the WG shall seek to act by consensus. The Chair may make a call for consensus. In making such a call, the chair should always make reasonable efforts to involve at a minimum all members of the WG. The chair shall be responsible for designating each position as having one of the following designations:

* Full Consensus - a position where no minority disagrees; identified by an absence of objection
* Consensus – a position where a small minority disagrees, but most agree

In the absence of Full Consensus, the Chair should allow for the submission of minority viewpoint(s) and these, along with the consensus view, shall be included in the report, paper or other relevant deliverable.

In rare cases, the Chair may decide to use of a poll to assess the level of support for a recommendation. However, care should be taken in using polls: they should not become votes, as there are often disagreements about the meanings of the poll questions or of the poll results. Such a poll shall be limited to the members, unless the chair decides otherwise.

Any person on the WG who disagrees with the consensus-level designated by the Chair, or believes that her/his contributions have systematically been ignored or discounted, should first discuss the circumstances with the Chair. If the matter cannot be resolved satisfactorily, the person should discuss the situation with the Chair of the ccNSO or a person designated by the Chair of the ccNSO.

If no consensus can be reached by the WG, the Chair of the WG will submit a Chair’s Report to the ccNSO Council and Issue Manager. In this report the Chair shall document the issues that are considered contentious, the process that was followed to try to reach a consensus position and suggestions to mitigate those issues, if any. If, after implementation of the mitigating measures, consensus still cannot be reached, the Chair shall prepare a Final Chair’s Report documenting the processes that was followed to reach consensus and this Final Chair’s Report will be deemed to replace the Final Paper. In this case, the ccNSO Council, advised by the Issue Manager, may decide to close the WG, or take mitigating measures, for example changing the charter and reconstitute a WG based on the new charter.

**3.3 Standards of Behaviour**

The persons on the WG are expected to behave in a mature and professional way when conducting its business. This includes, but is not limited to communicating with the fellow membership professionally and ensuring that the WG remains inclusive and productive. To resolve incidents of non-professional communication the following steps should be followed:

## Any concerns regarding the behaviour of one of the members, participants, observers or experts should first be raised with that person.

## If the issue is not satisfactorily resolved, a formal complaint may be raised with the Chair of the WG, who will attempt to mediate.

## If that is not possible, or if the complaint is sufficiently serious in nature, the Chair of the WG is empowered to restrict the participation of the person if in the chairs view the continued participation would not be appropriate and/or would seriously disrupt the working group from conducting its business.

## Generally, a person should first be warned privately, and then warned publicly before such the restriction is put into effect; only in extreme circumstances to be determined by the chair and vice-chair together, this restriction may be put in effect immediately.

If a WG Member disagrees with an imposed restriction, or the complainant disagrees with a restriction (or the lack of one), or there are other matters regarding the complaint that cannot be resolved satisfactorily, the participant, complainant, or the Chair of the WG may raise the issue with the Chair and Vice-Chairs of the ccNSO Council or their designate(s). They will review the matter and then decide. The ccNSO Council, WG Chair, WG person and complainant shall be informed accordingly.

4. Deliverables

4. 1. Working Method & Work Plan

The WG is expected to develop its working methods and a work plan first. The working methods should provide guidance on how the WG intends to conduct its business (see section 3.1). The work plan should include at a minimum, where feasible, timelines and expected outputs of the WG, based on the deliverables outlined in this Charter. Purpose of the work plan is to inform the community and ccNSO on the expected progress and anticipated schedule of public consultations.

Once the work plan is completed, the Time Line as set forth in section 6 shall be updated and published. If in the course of conducting its business the WG or the chair of the WG is of the view that the Time Line is untenable, the chair will inform the ccNSO Council and Issue Manager. The chair will then also suggest an adjusted Time Line to be adopted by the WG. Once adopted, the chair will inform the ccNSO Council and Issue Manager and the adjusted Time Line will be published.

4.2 WG Interim Paper

The WG shall develop and publish for public consultation an Interim Paper, which shall, at a minimum, include proposals to address the topics and issues identified in the Issue Report, an impact analysis of the proposals and any documentation necessary to make the proposals effective. The Interim Paper shall also contain a review and analysis of comments made on the Issue Report, if any, with respect to the retirement of ccTLDs. The Interim Paper shall be published for public consultation on the ICANN website following the guidelines for public consultations. The consultation should be scheduled in such a manner that it also allows for a public discussion with the relevant stakeholders at a designated ICANN meeting. The chair of the WG will send the Interim Paper to the Issue Manager of the ccPDP.

4.3 WG (draft) Final Paper

After conclusion of the public consultation on the Interim Paper, the WG shall prepare a (draft) Final Paper reflecting the Interim Paper, the comments received on the Interim Paper from the public consultation period.

If the WG is of the view that an additional public consultation is appropriate, it will prepare a draft Final Paper to be published for public consultation on the ICANN website and following the guidelines for public consultations. The consultation should be scheduled in such a manner that it also allows for a public discussion with the relevant stakeholders at a designated ICANN meeting. After conclusion of the public consultation on the draft Final Paper, the WG shall prepare its Final Paper that reflects the draft Final Paper, the comments received and how they have been taken into consideration by the WG, if at all.

The Final Paper will include the proposed policy recommendations. This Final Paper shall be published within fourteen (14) days after adoption of the paper by the WG and conveyed to the chairs of the ccNSO and GAC and the Issue Manager of the ccPDP. The Issue Manager shall include the Final Paper in the Interim Report of the ccPDP.

# **5 Miscellaneous**

**5.1 Omission in or unreasonable impact of Charter**

If this charter does not provide sufficient guidance and/or the impact of the charter is found to be unreasonable for conducting the business of the WG, the Chair has the authority to determine a proper course of action to mitigate the issue. Such action may, for example, consist of a modification to the Charter to address the omission or its unreasonable impact, in which case the Chair(s) may propose such modification to the ccNSO Council and Issue Manager. A modification shall only be effective after adoption of the amended by the ccNSO and after publication of the amended Charter. The chair of the WG shall exercise reasonable discretion with respect to question as to whether this charter does not provide guidance and/or the impact of the charter is unworkable with respect to the conduct of business of the WG.

## **5.2 Closure of the Working Group**

If the WG determines that it has completed its work, or if the WG cannot achieve its goal(s) the Final Chair Report, it will submit a Final Paper to the ccNSO Council and Issue Manager. This report should include a recommendation on the time to close the WG.

A WG is closed by a resolution of the ccNSO Council.

6. WG Time Line

|  |  |  |  |
| --- | --- | --- | --- |
| **Activity** | **Date\*** | **Closure\*** | **Minimum Duration** |
| **Establishment of Working Group** |  |  |  |
| **Publish Interim Report** |  |  | NA |
| **Public Comment on Interim Paper** |  |  | 40 days |
| **Publish Final Paper** |  |  | NA |
| **Closure of the WG** |  |  |  |

\* Latest date possible to meet minimum duration for public consultation period.

\*\* It is assumed in this schedule / time line the Final Paper is presented at an ICANN meeting.

7. References

* RFC 1591 (<https://www.ietf.org/rfc/rfc1591.txt> )
* The ccNSO Delegation and Redelegation working group Final report on retirement of ccTLDs, 07 march 2011 (<http://ccnso.icann.org/workinggroups/drd-wg-retirement-report-07mar11-en.pdf)>
* The ccNSO Framework of Interpretation working group Final Report, (<http://ccnso.icann.org/workinggroups/foi-final-07oct14-en.pdf> )
* ISO 3166 standard (<http://www.iso.org/iso/country_codes)>
* CWG-Stewardship Final Report, Annex O: ccTLD Appeals Mechanism Background and supporting Findings Sections 1414- 1428, (<https://community.icann.org/download/attachments/53779816/FinalTransitionProposal_11June.pdf?version=1&modificationDate=1434047705000&api=v2> ).
* Relevant IANA reports on the Retirement of ccTLDs.
* Issue paper retirement ccTLDs : <https://community.icann.org/download/attachments/64068742/Issues%20to%20explore%20and%20define%20with%20respect%20to%20the%20retirement%20of%20ccTLDs-%20v3.pdf?version=1&modificationDate=1491820583082&api=v2>

**Annex C: Detailed Schedule and Timeline**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Event** | | **Entity** | **Tentative Date completion** | **Comment** |
| **1** | **Draft Issue Report** |  | Issue Manager | March 2017 | To be presented to the Council for its Copenhagen meeting |
| **Initiation PDP** | | | | | |
| **2** | **Formal Decision to initiate the ccPDP** |  | ccNSO Council | March 2017 | ccNSO Council vote |
| **Comments on Issue PDP** | | | | | |
| **3** | **Comments on Issue PDP** | **Public notification of Initiation of ccPDP** | Issue Manager | March 2017 | Notification of initiation of the ccPDP on the ICANN Website and to the other ICANN Supporting Organizations and Advisory Committees. Open comment period (in accordance with the PDP Time Line. At least 40 days long) shall be commenced for the issue. |
| **4** |  | **Call for Volunteers** | Issue Manager | March 2017 |  |
| **5** |  | **Formal request to Chair of the GAC to offer opinion or advice** | ccNSO Council | March 2017 |  |
| **6** |  | **Formation of Working Group I under ccPDP**  **Call for volunteers, invite participants** | ccNSO Council | March 2017 | As part of the ccPDP, create a Working Group to propose and develop policy for Review Mechanism |
| **Preparing Recommendations** | | | | | |
| **7** |  | **Appointment members, chair** | Council | May 2017 | With appointment of chairs etc, kick-off second phase PDP |
| **8** |  | **Interim Paper** | ccPDP WG I | October 2017 | To be published in time to be discussed at ICANN meeting and public comment |
| **9** |  | **Formation WG II, Call for volunteers, appointment etc.** | ccNSO Council | December 2017 | Call for volunteers WG 2 Retirement of ccTLDs,  Self-nominations, invite ALAC, GAC, GNSO and, SSAC to appoint at least one participant.  Invite Regional Organisations to appoint at least 1 participant.  Invite PTI staff and expert on ISO 3166. |
| **10** |  | **Update Paper WG I** | ccPDP  WG I | January 2018 | Interim paper on Review Mechanism will need to be updated to take into account the public comments. |
|  |  | **Hibernation of WG I** | ccNSO Council | January 2018 | WG 1 will recommence its work after WG 2 has fished its work to update the proposal to incorporate |
| **11** |  | **Interim Paper WG 2** | ccPDP WG 2 | May 2018 | Interim paper for public comment on Retirement of ccTLDs |
| **12** |  | **Final Paper WG 2** | ccPDP WG 2 | October 2018 | Submission Final Paper to Issue Manager and chair of WG 1. |
| **13** |  | **Closure of Working Group 2** |  | October 2018 |  |
| **14** |  | **Draft Final Paper WG 1** | WG 1 | January 2019 | Review and update proposal WG 1, based on final paper WG 2. Open for public comment. |
|  |  | **Final Paper WG 1** |  | March 2019 | Submission Final Paper to Issue Manager. |
| **15** |  | **Initial Report ccPDP** | Issue Manager | March 2019 | Initial Report of IM. This report consolidates final recommendations WG 1 and WG 2 into one report. Needs to be published in time for full discussion at ICANN meeting and public comment |
| **16** |  | **Final Report** | Issue Manager | May 2019 | Final Report of the ccPDP. This contains the recommendations to resolve issues as identified in Issues Report and will be submitted to the Council. This step initiates the decision making process. |
| **ccNSO Decision making phase** | | | | | |
| **18** |  | **Submission of Final Report to the ccNSO Council** | Issue Manager | May 2019 |  |
| **19** |  | **Invite the Chair of the GAC to offer opinion or advice** | ccNSO Council | May 2019 | Formal step as defined for the ccPDP |
| **20** |  | **ccNSO Council Adoption of Final Report** | ccNSO Council | June 2019 | Decision ccNSO Council |
| **21** |  | **ccNSO members vote** | ccNSO Members | July or September 2019 | Final vote of the ccNSO members |
| **22** |  | **Board Report** | ccNSO Council | October 2019 | Conclude the ccNSO Decision making |
| **Board Decision making Phase** | | | | | |
| **23** |  | **Submission**  **Board report** | Issue Manager | October 2019 |  |

**Postscript**

At its meeting on 15 March 2017 the ccNSO Council adopted the following resolution:

**ccNSO Council Resolution on ccPDP 3**

**ccNSO Policy Development Process on introduction of a Review Mechanism and Retirement of country code Top Level Domains**

15 March 2017

**Background**

At its meeting on 10 December 2015 the ccNSO Council discussed the launch of the formal ccNSO Policy Development Processes to address the lack of policy with respect to retirement of ccTLDs and Review Mechanism on issues of delegation, revocation and retirement of ccTLDs.

To increase the predictability and legitimacy of decision pertaining to the retirement of ccTLDs and in accordance with the recommendations of the ccNSO Delegation and Redelegation working group (DRDWG) in 2011[[24]](#footnote-24), the void or lack of policy relating to the retirement of ccTLDs needs to filled by a policy developed by the ccNSO. However, at the time the DRDWG also recommended that such a ccNSO PDP should be launched following the development of a Framework of Interpretation of RFC 1591.

Assuming the IANA Stewardship Transition will be successful, a Review Mechanism should be in place rather sooner than later to ensure a redress mechanism for ccTLDs with respect to the most critical decisions pertaining to ccTLDs: delegation, revocation, transfer and retirement of a ccTLD. Until such time a policy this has been developed and is implemented, such a mechanism remains unavailable, whilst comparable decisions or similar decisions affecting gTLDs are subject to review and redress.

Following the initial discussions of Council, input and feed-back was sought from the community at the Marrakesh and Helsinki meetings. The community present was of the view that the initial focus needs to be on developing a Review Mechanism, which is considered the highest priority, in particular in light of the IANA Stewardship transition. Only then the focus should on retirement, and, if needed, revisit the Review Mechanism to include decisions relating to the retirement of ccTLDs.

At its meeting in Helsinki (ICANN 56) the ccNSO Council ccNSO Council requests an Issue Report, which should address the following topics:

* 1. Recommend whether the ccNSO should initiate the ccNSO Policy Development Process on the retirement of ccTLDs and review mechanism for decision pertaining to the delegation, transfer, revocation and retirement of ccTLDs.
  2. Advice whether or not to initiate a ccPDP to develop a policy on Review Mechanism first and defer the decision on the Retirement to a later stage, and if so, when the decision should be taken.
  3. Advise whether to convene a Taskforce or use other method
  4. If recommended to initiate to a ccNSO Policy Development Process a proposed time line for conducting each of the stages of PDP outlined herein (PDP Time Line)

Following the discussion with the community present at the Hyderabad meeting on the topics to be dealt with through a ccPDP, and at the request of the Issue Manager, the ccNSO Council called for one or two drafting teams which would develop charters of the working groups to:

* Develop the review mechanism of decision pertaining to the delegation, transfer, revocation and retirement of ccTLDs and
* Develop recommendations for a policy on the retirement of ccTLDs.

The draft charters should be included in the Issue Report.

On 9 March 2017, the Issue Manager submitted the Final Issue Report to Council.

Following the discussions within the Council, feed-back and input from the community and the drafting team, the Issue Manager recommended:

1. The ccNSO Council initiates a ccNSO Policy Development Process to develop policies for a Review Mechanism and on the retirement of ccTLDs.
2. To initiate one (1) ccNSO Policy Development Process. It is further recommended that the initial focus needs to be on developing a Review Mechanism, which is considered the highest priority, particularly in light of the IANA Stewardship transition. Only then the focus should be on retirement, and, if needed, revisit the Review Mechanism to include decisions relating to the retirement of ccTLDs.
3. To appoint two working groups each with its own charter, working method and schedule.

However, at the meeting in Copenhagen community members suggested to change the order in which the topics need to be addressed. Analyses shows that such an alternative order safe at least 3 months and simplify the process. Effectively this means that by reversing the order, so first retirement and then review mechanism, the potential review mechanism would be available sooner to the community.

Finally, as already noted in 2011 the retirement of ccTLDs has been and is undertaking with no policy in place. As the ccNSO will embark on the development of a policy for the retirement of ccTLDs, and pending the outcome of this process, new decisions in this area could impact the development of such a policy and are taken with the knowledge that a policy is being developed.

**Decisions**

1. **In accordance with Annex B section 3and 4 of the ICANN Bylaws, the ccNSO Council decides that:**
2. **Based on a review of the issues, considering that the Threshold Criteria are met, and taking into account General Counsel’s opinion, the Issues Manager recommendation to initiate one (1) ccNSO Policy Development Process to develop policies for a Review Mechanism and on the retirement of ccTLDs.**
3. **The initial focus needs to be on developing a policy for Retirement of ccTLDs, and only after the substantive work has been concluded the focus should be on developing recommendations pertaining to the Review Mechanism pertaining to decisions on delegation, transfer, revocation and retirement of ccTLDs.**
4. **To appoint two working groups each with its own charter, working method and schedule.**

1. **The secretariat is requested to send out a call for volunteers for the first WG, and invite other stakeholders listed in the relevant charter, to participate in the WG in the manner most suited to them.**
2. **As required under Annex B, the Chair of the ccNSO is requested to formally inform the Chair of the GAC and ask the GAC to advise or provide an opinion.**
3. **The chair of the ccNSO is requested to recommend the ICANN Board of Directors to defer any decisions pertaining to the retirement of a ccTLD until such a time the policy for the retirement of the ccTLD has been developed following this ccNSO PDP 3 and adopted and implemented by ICANN.**
4. **The secretariat is requested is publish this resolution as soon as possible and upon publication it becomes effective.**

**Adjusted timeline to reflect adopted order of work items**

**(Retirement WG first to be followed by review mechanism WG)**

**Detailed Schedule and Timeline retirement first then review mechanism**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Event** | | **Entity** | **Tentative Date completion** | **Comment** |
| **1** | **Draft Issue Report** |  | Issue Manager | March 2017 | To be presented to the Council for its Copenhagen meeting |
| **Initiation PDP** | | | | | |
| **2** | **Formal Decision to initiate the ccPDP** |  | ccNSO Council | March 2017 | ccNSO Council vote |
| **Comments on Issue PDP** | | | | | |
| **3** | **Comments on Issue PDP** | **Public notification of Initiation of ccPDP** | Issue Manager | March 2017 | Notification of initiation of the ccPDP on the ICANN Website and to the other ICANN Supporting Organizations and Advisory Committees. Open comment period (in accordance with the PDP Time Line. At least 40 days long) shall be commenced for the issue. |
| **4** |  | **Call for Volunteers** | Issue Manager | March 2017 |  |
| **5** |  | **Formal request to Chair of the GAC to offer opinion or advice** | ccNSO Council | March 2017 |  |
| **6** |  | **Formation of Working Group I under ccPDP**  **Call for volunteers, invite participants** | ccNSO Council | March 2017 | As part of the ccPDP, create a Working Group to propose and develop policy for Retirement. Self-nominations, invite ALAC, GAC, GNSO and, SSAC to appoint at least one participant.  Invite Regional Organisations to appoint at least 1 participant.  Invite PTI staff and expert on ISO 3166. |
| **Preparing Recommendations** | | | | | |
| **7** |  | **Appointment members, chair** | Council | May 2017 | With appointment of chairs etc, kick-off second phase PDP |
| **8** |  | **Interim Paper** | ccPDP WG I Retirement | October 2017  At least 40 days public comment period | To be published in time to be discussed at ICANN meeting and public comment |
| **9** |  | **Formation WG II, Call for volunteers, appointment etc.** | ccNSO Coucil | December 2017 | Call for volunteers WG 2 Review Mechanism  Self-nominations, invite ALAC, GAC, GNSO and, SSAC to appoint at least one participant.  Invite Regional Organisations to appoint at least 1 participant.  Invite PTI staff and expert on ISO 3166. |
| **10** |  | **Update Paper WG I** | ccPDP  WG I | January 2018 | Interim paper on Retirement will need to be updated to take into account the public comments. |
|  |  | **Final Paper Retirement** | ccPDP WG 1 | January 2018 | WG 1 to submit final paper to IM |
| **11** |  | **Interim Paper WG 2**  **Review Mechanism** | ccPDP WG 2 | May 2018  At least 40 days public comment | Interim paper for public comment on Review Mechanism |
| **12** |  | **Final Paper WG 2** | ccPDP WG 2 | October 2018 | Submission Final Paper to Issue Manager and chair of WG 1. |
| **14** |  | **Initial Report ccPDP** |  | October 2018  40 days public comment | Initial Report of IM. This report consolidates final recommendations WG 1 and WG 2 into one report. Needs to be published in time for full discussion at ICANN meeting and public comment. |
| **15** |  | **Final Report** | Issue Manager | February/March 2019 | Final Report of the ccPDP. This contains the recommendations to resolve issues as identified in Issues Report and wil be submitted to the Council. This step initiates the decision making process. |
| **ccNSO Decision making phase** | | | | | |
| **18** |  | **Submission of Final Report to the ccNSO Council** | Issue Manager | February/March 2019 |  |
| **19** |  | **Invite the Chair of the GAC to offer opinion or advice** | ccNSO Council | February/March 2019 | Formal step as defined for the ccPDP |
| **20** |  | **ccNSO Council Adoption of Final Report** | ccNSO Council | March 2019 | Decision ccNSO Council |
| **21** |  | **ccNSO members vote** | ccNSO Members | April 2019 | Final vote of the ccNSO members |
| **22** |  | **Board Report** | ccNSO Council | June 2019 | Concludes the ccNSO Decision making |
| **Board Decision making phase** | | | | | |
| **23** |  | **Submission**  **Board report** | Issue Manager | June 2019 |  |

1. The term “Review Mechanism” has been chosen to differentiate from the appeals process referred to in RFC1591 relating to the review of decisions relating to delegation, transfer and revocation of a ccTLD, from the generic Independent Review Process (IRP) as required by the CCWG- Accountability group for appeals / reviews on other decisions. [↑](#footnote-ref-1)
2. See DRD WG Final Report, page 19, <http://ccnso.icann.org/workinggroups/drd-wg-final-report-07mar11-en.pdf> and Council Decision 16 March 2011, <http://ccnso.icann.org/workinggroups/minutes-council-16mar11-en.pdf> [↑](#footnote-ref-2)
3. The more detailed topic paper can be found at: <https://community.icann.org/display/ccnsowkspc/Documents> [↑](#footnote-ref-3)
4. Section 3.4 RFC 1591 is about the definition and role of Significantly Interested parties. [↑](#footnote-ref-4)
5. The CCWG- Accountability also proposes that the IRP:

   *Be subject to certain exclusions relating to the results of an SOs policy development process, country code top- level domain delegations/ redelegations, numbering resources, and protocols parameters.* See: page 33 <https://www.icann.org/en/system/files/files/ccwg-accountability-supp-proposal-work-stream-1-recs-23feb16-en.pdf> [↑](#footnote-ref-5)
6. https://www.icann.org/resources/pages/governance/bylaws-en/#article4 [↑](#footnote-ref-6)
7. <https://ccnso.icann.org/workinggroups/drd-wg-retirement-report-07mar11-en.pdf> [↑](#footnote-ref-7)
8. The retirement process of .AN was completed in 2015, see <http://www.iana.org/domains/root/db/an.html>

   The retirement process of .TP was completed in 2015, see <http://www.iana.org/domains/root/db/tp.html> [↑](#footnote-ref-8)
9. This is language that is not included in the official standard, but for illustration from the ISO 3166 website: <http://www.iso.org/iso/country_codes_glossary.html> [↑](#footnote-ref-9)
10. https://www.icann.org/resources/pages/governance/bylaws-en/#annexC [↑](#footnote-ref-10)
11. https://www.ietf.org/rfc/rfc1591.txt [↑](#footnote-ref-11)
12. See DRD WG Final Report, page 19, <http://ccnso.icann.org/workinggroups/drd-wg-final-report-07mar11-en.pdf> and Council Decision 16 March 2011, <http://ccnso.icann.org/workinggroups/minutes-council-16mar11-en.pdf> [↑](#footnote-ref-12)
13. https://ccnso.icann.org/workinggroups/charters.htm [↑](#footnote-ref-13)
14. The term “Review Mechanism” has been chosen to differentiate from the appeals process referred to in RFC1591 relating to the review of decisions relating to delegation, transfer and revocation of a ccTLD, and from the generic Independent Review Process (IRP) as required by the CCWG- Accountability group for appeals / reviews on other decisions. [↑](#footnote-ref-14)
15. Section 3.4 RFC 1591 is about the definition and role of Significantly Interested parties. [↑](#footnote-ref-15)
16. The CCWG- Accountability also proposes that the IRP:

    *Be subject to certain exclusions relating to the results of an SOs policy development process, country code top- level domain delegations/ redelegations, numbering resources, and protocols parameters.* See: page 33 <https://www.icann.org/en/system/files/files/ccwg-accountability-supp-proposal-work-stream-1-recs-23feb16-en.pdf> [↑](#footnote-ref-16)
17. https://www.icann.org/resources/pages/governance/bylaws-en/#article4 [↑](#footnote-ref-17)
18. <https://ccnso.icann.org/workinggroups/foi-final-07oct14-en.pdf>, page 3. [↑](#footnote-ref-18)
19. https://ccnso.icann.org/about/guidelines-working-groups-30mar16-en.pdf [↑](#footnote-ref-19)
20. <https://ccnso.icann.org/workinggroups/drd-wg-retirement-report-07mar11-en.pdf> [↑](#footnote-ref-20)
21. The retirement process of .AN was completed in 2015, see <http://www.iana.org/domains/root/db/an.html>

    The retirement of .TP was completed in 2015 as well, see <http://www.iana.org/domains/root/db/tp.html> [↑](#footnote-ref-21)
22. This is language that is not included in the official standard, but for illustration from the ISO 3166 website: <http://www.iso.org/iso/country_codes_glossary.html> [↑](#footnote-ref-22)
23. https://ccnso.icann.org/about/guidelines-working-groups-30mar16-en.pdf [↑](#footnote-ref-23)
24. See DRD WG Final Report, page 19, <http://ccnso.icann.org/workinggroups/drd-wg-final-report-07mar11-en.pdf> and Council Decision 16 March 2011, <http://ccnso.icann.org/workinggroups/minutes-council-16mar11-en.pdf> [↑](#footnote-ref-24)