## Slide 2: IANA Functions Contract Expires
1 October 2016: The contract between ICANN and the U.S. National Telecommunications and Information Administration (NTIA), to perform the IANA functions, officially expired.

## Slide 3: Committing to Further Accountability Work in Work Stream 2
As part of Work Stream 2, the CCWG-Accountability proposes that further enhancements be made to a number of designated mechanisms and processes and to refine the operational details associated with some of its recommendations for Work Stream 1.
It is intended that Work Stream 2 will be completed by June 2017
WS2 Topics
Diversity
Human Rights
Jurisdiction
SO/AC Accountability
Ombudsman
Transparency
Staff Accountability
Guidelines for standards of conduct presumed to be in good faith associated with exercising removal of individual ICANN Board Directors
Reviewing the Cooperative Engagement Process (CEP)

## Slide 4: Work Stream 2 Timeline
The chart outlines the anticipated work flow for CCWG WS2 Subgroups and Plenary sessions in order to complete the work by the anticipated due date, June 2017.
Sep
Oct
Nov
Dec
Jun
May
Mar
Feb
Jan
Kick-off
Scope and Work Plan
Development
Finalization
Jul
Aug
Apr
ICANN 57
Hyderabad
ICANN 58
Copenhagen
ICANN 59
Johannesburg
Public Comment Period
Public Comment Period
Ombudsman
SO/AC Acct.
Staff Acct.
Guidelines…..
Human Rights
Jurisdiction
Transparency
Diversity
CEP

## Slide 5
| 3
Apr May Jun
Updated on: 01 Nov 16
WS2 Monthly Activity Update
Nov Dec
On-track
Behind schedule, but recovery still possible
Jan Feb
Not started
Target will be missed
Completed
Jul Aug Sep
Oct
Mar
Kick-off
Scoping
Public Comments
Overall Timeline*:
(*) work plans may vary by
subgroup.
CCWG Plenary & Subgroups Monthly Activity:
ICANN 57
ICANN 58
ICANN 59
CCWG
discussion
Subgroup
produces draft
Subgroup
analyzes PC
/revises output
Subgroup produces draft
Analyze comments
/revises output
Scoping
CCWG
discussion
CCWG
review
CCWG
review
TRACK 1
•Human Rights
•Jurisdiction
• Transparency
• Diversity
•CEP
TRACK 2
•Ombudsman
•SO/AC Acct.
•Staff Acct.
• Good Faith…..
Present final recommendations
Report date
Public Comments
Reporting Period:
OCTOBER 16
July to October Participation in Calls/Meetings by Affiliation:
53%
55%
37%
0
5
10
15
20
25
450
400
350
300
250
200
150
100
50
0
Jul Aug
# of emails
# of meetings
Sep Oct Nov Dec Jan Feb Mar Apr May Jun
Average # of community members attending calls (including observers, excluding ICANN staff). Participation rate: average of subgroups and plenary monthly participation rates (active participants/signed-up participants)
Meetings & Attendees
Emails
CCWG
review
CCWG
review
Signed-up participants (excluding observers) Meetings attendees (all)
70%
60%
50%
40%
30%
20%
10%
0%

## Slide 6
Updated on: 01 Nov 16 | 4
Subgroups Progress Update
Topic
# of Meetin gs held this month
Progress
Status
Updates
Focus / Concerns / Risks
Diversity
3
Been reviewing a strawman document prepared by the co-rapporteurs in an effort to define the scope.
Questions raised by rapporteurs are being discuss
within the group.
Human Rights
4
Documented the historical context. Analyzed the UN Guiding Principles for Business and HRs. Developed a draft structure for the FOI-HR. Formed drafting team.
Focus on the definition of:
  'respecting human rights'
  'applicable law'
Jurisdiction
4
Discussed ICANN’s incorporation and headquarters
location jurisdiction
Defining and examining ICANN’s Multiple Layers of Jurisdiction
Clarify what the “gap analysis” referred to in
Annex 12 is.
Balance focus/scope with multiplicity of potential topics relating to “jurisdiction”.
SO/AC
Accountability
3
The following documents have been prepared and distributed:
Pro p o sed ‘ Qu estio n s for AC/SOs’
SOAC-ACC-Pro gress Rep o rt Oct’ 16
Track 2: divergence of views among participants on the matter of Mutual Accountability will be addressed after other aspects of our work plan are more complete.
Staff Accountability
1
Collated lists of information required
In early stages of gathering information
Set of questions sent to staff about staff accountability mechanisms
Transparency
1
Developed a draft Report, including Rec’s.
Report presented to the subgroup on Oct 21 and
circulated to the CCWG for first reading on Oct 25.
All Recommendations are still being discussed.
Require significant more examination of ICANN’s
proactive disclosure policies.
Ombudsman
3
Report for Hyderabad
Coordination with other sub-groups (Transp.,
Staff Account., H.Rights, Div., SO/AC Account.)
ICANN Staff Complains Officer vs IOO
Review of the
CEP
1
Two sub-units formed, Bylaws and CEP Rules and procedures, with Anna Loup (Bylaws) and Farzaneh Badii (Rules) volunteering to assist the Rapporteur in scoping these areas of inquiry.
Bolster the subgroup's expertise
Relationship between the IRP and CEP
Creation of CEP Rules
Good Faith
Conduct
2
Differentiated between removal of Nom Com and SO/AC appointees to Board
Draft guidelines distributed to plenary for initial reaction
Request for legal support submitted to secretariat
Challenges around use of the word “cause” in the ICANN context
Is process fair/reasonable if expectations cannot be
expressed beyond “do no harm”?
On-track
Behind schedule, but recovery still possible
Target will be missed
Not started
Completed
Reporting Period:
OCTOBER 16
10%
(+ - %)
25%
(+ - %)
15%
(+ - %)
35%
(+ - %)
20%
(+ - %)
40%
(+ - %)
15%
(+ - %)
20%
(+ - %)
(+ - %)
10%
Progress:
22%