## Slide 2
IANA Stewardship Transition
Trang Nguyen | 6 November 2016

## Slide 3: IANA Stewardship Transition Implementation Timeline & Status
 | Nov ‘15 | Dec ‘15 | Jan ‘16 | Feb ‘16 | Mar ‘16 | Apr ‘16 | May ‘16 | Jun ‘16 | Jul ‘16 | Aug ‘16 | Sep ‘16 | Oct ‘16 | Nov ‘16
ICANN
55
ICANN
56
Root Zone Management System (RZMS) updates & parallel testing
Root Zone Maintainer Agreement (RZMA)
Service Level Expectations (SLEs) for Naming Community
Service Level Agreements (SLAs) with the Number Community
IETF MoU Supplemental Agreement
Customer Standing Committee (CSC)
ICANN Bylaws
Independent Review Process (IRP) Enhancements
Reconsideration Request Enhancements
Empowered Community
Naming and Services agreements
IANA Intellectual Property Rights (IPR)
Root Zone Evolution Review Committee (RZERC)
IANA Operational Escalation Processes
Implementation of the post-transition Financial Planning Process
Tasks Completed to Allow the IANA Functions Contract to Expire
Track 1
Track 2
Track 3
ICANN Articles of Incorporation
✔
Incorporation, Bylaws, Governance Docs, Subcontracting Agreements
Public Technical Identifiers (PTI)
✔
✔
✔
✔
✔
✔
✔
✔
✔
✔
✔
✔
✔
✔
Phase 2
NTIA contract expiration
ICANN
57

## Slide 4: First-Level Direct Relationship of Existing and New Structures to ICANN
*Names
Oversight
Contract
Bylaws
ICANN Board
PTI Board
NomCom
SOs
ACs
CSC*
RZERC
Verisign
RiRs
IETF
EC
IETF Trust
Ombudsman
Existing
New
PTI
(Controlled Affiliate of ICANN)
ICANN
*Names only

## Slide 5: First-Level Direct Relationship of Existing and New Structures to ICANN
*Names
Oversight
Contract
Bylaws
ICANN Board
PTI Board
NomCom
SOs
ACs
CSC*
RZERC
Verisign
RiRs
IETF
EC
IETF Trust
Ombudsman
Existing
New
PTI
(Controlled Affiliate of ICANN)
ICANN
*Names only

## Slide 6: First-Level Direct Relationship of Existing and New Structures to ICANN
*Names
Oversight
Contract
Bylaws
ICANN Board
PTI Board
NomCom
SOs
ACs
CSC*
RZERC
Verisign
RiRs
IETF
EC
IETF Trust
Ombudsman
Existing
New
PTI
(Controlled Affiliate of ICANN)
ICANN
*Names only

## Slide 7: First-Level Direct Relationship of Existing and New Structures to ICANN
*Names
Oversight
Contract
Bylaws
ICANN Board
PTI Board
NomCom
SOs
ACs
CSC*
RZERC
Verisign
RiRs
IETF
EC
IETF Trust
Ombudsman
Existing
New
PTI
(Controlled Affiliate of ICANN)
ICANN
*Names only

## Slide 8: First-Level Direct Relationship of Existing and New Structures to ICANN
*Names
Oversight
Contract
Bylaws
ICANN Board
PTI Board
NomCom
SOs
ACs
CSC*
RZERC
Verisign
RiRs
IETF
EC
IETF Trust
Ombudsman
Existing
New
PTI
(Controlled Affiliate of ICANN)
ICANN
*Names only

## Slide 9: First-Level Direct Relationship of Existing and New Structures to ICANN
*Names
Oversight
Contract
Bylaws
ICANN Board
PTI Board
NomCom
SOs
ACs
CSC*
RZERC
Verisign
RiRs
IETF
EC
IETF Trust
Ombudsman
Existing
New
PTI
(Controlled Affiliate of ICANN)
ICANN
*Names only

## Slide 10: First-Level Direct Relationship of Existing and New Structures to ICANN
*Names
Oversight
Contract
Bylaws
ICANN Board
PTI Board
NomCom
SOs
ACs
CSC*
RZERC
Verisign
RiRs
IETF
EC
IETF Trust
Ombudsman
Existing
New
PTI
(Controlled Affiliate of ICANN)
ICANN
*Names only

## Slide 11: First-Level Direct Relationship of Existing and New Structures to ICANN
*Names
Oversight
Contract
Bylaws
ICANN Board
PTI Board
NomCom
SOs
ACs
CSC*
RZERC
Verisign
RiRs
IETF
EC
IETF Trust
Ombudsman
Existing
New
PTI
(Controlled Affiliate of ICANN)
ICANN
*Names only

## Slide 12: Engage
Drat PTI FY18 Operation Plan and Budget https://www.icann.org/public-comments/fy18-pti-operating-plan-budget-2016-10-24-en
Introduction to PTI session (Saturday, 1:45pm, Hall 2)
CSC face-to-face meeting (Tuesday, 8:30am, MR 1.03)

## Slide 13
Reviews

## Slide 14: Reviews: What is Coming Up
2016
Q1
Q2
Q3
Q4
Q1
Q2
JUL 2017
ccNSO2
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
2017
2018
2019
TODAY
SPECIFIC REVIEW
LEGEND:
ORG REVIEW
Q3
Q4
JUL 2014
GNSO2
OCT 2015
CCT
MAY 2016
At-Large2
OCT 2016
RDS (formerly WHOIS2)
JAN 2017
ATRT3
FEB 2017
NomCom2
APR 2017
RSSAC2
MAY 2017
ASO2
JUN 2017
SSAC2
Lines represent the Planning, Conducting, and Implementation phases of the Review process
JUL 2016
SSR2
Reviews: what is coming up

## Slide 15: What Do Reviews Mean Post-Transition?
More Power & More Responsibility for the Community
Operating Standards
Establish a roadmap
for Reviews
Less Frequency, More Impact
5 year Review cycle
Community Selection
Community leaders select Review Teams
Consistent, Efficient, & Effective

## Slide 16: Engage with ICANN
Reach us at:
Email: engagement@icann.org
Website: icann.org
Thank You and Questions
linkedin.com/company/icann
twitter.com/icann
facebook.com/icannorg
weibo.com/ICANNorg
youtube.com/user/icannnews
slideshare.net/icannpresentations
flickr.com/photos/icann
soundcloud.com/icann
Notes: You can adjust the email/web address to whichever email or web address is best suited to your presentation. This should be your final slide.